## Sheet1
C1 | 1.1 Ensure vendors (RFP) provide evidence (VPAT) of accessibility compliance | 1.2 Review the Project Manager Process | 1.3 Include Accessibility as a requirement | 1.7 Integrate both the manual test scripts and an appropriate automated testing solution. | 1.9 Include Colt accessibility strategy and legal risks in business case. | 2.3 Use Colt’s Accessibility Guidance to inform the techniques used. | 3.1a Ensure all Accessibility Testing has been successfully completed, and all bugs resolved or prioritised. | 3.4 Capture the test outcomes in a separate report to be archived in case of any legal challenges. | 5.1 Ensure Applicable Backlog and Reports are transferred to Operations | 5.4 Post Implementation. Prioritise backlog based on level of Risk identified in RAID.
PMO | Include/Enquire |  | Include/Enquire | [7 empty] | Include/Enquire
Business Owner | A |  | A | I | R+A | I | I | A | A | R+A | R | Responsible
Project Manager | R | R | C | I | I | I | I | C | R |  | A | Accountable
Test Manager | I |  | I | R+A | I | C | R+A | R |  | I | C | Consulted
Developer | I |  | I | C | I | R+A | C |  |  | I | I | Informed
Business Analyst | I |  | R | I | I | I | I |  |  | C |  | N/A
C2 | 0.4 Include Colt accessibility strategy and legal risks. | 1.5 Ensure the Accessibility Guidelines are included as they are a Legal requirement. | 1.7 Integrate both the manual test scripts and an appropriate automated testing solution. | 1.9 Include Colt accessibility strategy and legal risks in business case. | 2.3 Use Colt’s Accessibility Guidance to inform the techniques used. | 3.1a Ensure all Accessibility Testing has been successfully completed, and all bugs resolved or prioritised. | 3.4 Capture the test outcomes in a separate report to be archived in case of any legal challenges. | 5.1 Ensure Applicable Backlog and Reports are transferred to Operations | 5.4 Post Implementation. Prioritise backlog based on level of Risk identified in RAID.
PMO | Include/Enquire
Business Owner | A | A | I | R+A |  | I | A | A | R+A
Project Manager | R | C | I | I | I | I | C | R
Test Manager | I | I | R+A | I | C | R+A | R |  | I
Developer | I | I | C | I | R | C |  |  | I
Business Analyst | I | R | I | C | I | I |  |  | C
C3 | 0.4 Include Colt accessibility strategy and legal risks. | 1.5 Integrate both the manual test scripts and an appropriate automated testing solution. | 2.3 Use Colt’s Accessibility Guidance to inform the techniques used. | 3.1a Ensure all Accessibility Testing has been successfully completed, and all bugs resolved or prioritised. | 3.4 Capture the test outcomes in a separate report to be archived in case of any legal challenges. | 5.1 Ensure Applicable Backlog and Reports are transferred to Operations | 5.4 Post Implementation. Prioritise backlog based on level of Risk identified in RAID.
PMO | Include/Enquire
Business Owner | A | I |  | I | A | A | R+A
Project Manager | R | I | I | I | C | R
Test Manager | I | R+A | C | R+A | R |  | I
Developer | I | C | R | C |  |  | I
Business Analyst | I | I | I | I |  |  | C